## DAILY
Company: | Dragados | [5 empty] | Date: | 0
Project: | JWPCP Effluent Outfall Tunnel | [5 empty] | Weather: | Sunny |  |  | DAY | #REF!
Location: | JWPCP Site | [5 empty] | Site Conditions: | Normal
|  | No. of Days Worked on Project: | 0 |  |  |  | Temp: | 0
[12 empty] | 1 | 2 | 3 | #REF!
Dragados Staff* |  |  | Dragados Personnel |  |  |  | Subcontractors Onsite |  |  |  | Description | DAY | SWING | GRAVEYARD | MISSING (-)
Office Staff | 234 |  | Foreman | 34 |  |  | WA RASIC | 324 |  |  | Foreman | 1 | 1 | 1 |  | 1
Field Staff | 243 |  | Operators | 234 |  |  | TENSA | 243 |  |  | Electricians | #REF! | #REF! | #REF! |  | 6
Safety | 243 |  | Laborers | 24 |  |  | TEI | 2344 |  |  | Laborers | #REF! | #REF! | #REF! |  | 15
|  |  | Cr Operators | 234 |  |  | Sixense | 243 |  |  | Gas Tester | #REF! | #REF! | #REF! |  | 1
|  |  | Mechanics | 234 |  |  | Landmark | 243 |  |  | Mechanics | #REF! | #REF! | #REF! |  | 4
|  |  | Oiler | 423 |  |  | Guard | 24 |  |  | Operators | #REF! | #REF! | #REF! |  | 1
|  |  | Gas Tester | 32 |  |  | District | 234 |  |  | Cr Operator | #REF! | #REF! | #REF! |  | 1
|  |  | Surveyor | 23 |  |  | HK | 243 |  |  | Oiler | #REF! | #REF! | #REF! |  | 1
[7 empty] | Ballard | 234 |  |  | Surveyor | #REF! | #REF! | #REF!
Dragados Production Details |  |  |  |  | Shift Start: |  | 14:00 | Shift End: | 22:00
Description of Work Performed |  |  |  |  | TBM ADVANCE | [11 empty] | r
[5 empty] | START STA |  | 0
[5 empty] | END STA |  | 0
[6 empty] | SHIFT |  | DAILY TOTAL
[5 empty] | ADVANCE | 43 |  | 44 |  | 1
[5 empty] | RINGS BUILT | 34 |  | 57 |  | 23
[5 empty] | PT THREADED | 34 |  | 38 |  | 4
[5 empty] | PT TENSIONED | 43 |  | 77 |  | 34
[5 empty] | PT GROUTED | 23 |  | 28 |  | 5
TBM GREASE CONSUMPTION
[5 empty] | Grease Station | Δ Filling Level (mm) |  | Weight (KG)
[5 empty] | TSG 1 | 234 |  | 82.9787
[5 empty] | TSG 2 | 234 |  | 82.9787
[5 empty] | EP2 | 243 |  | 65.4894
[5 empty] | HBW | 234 |  | 76.3404
Equipment
[5 empty] | No. |  | Description
[5 empty] | 2 |  | Crane (Liehberr 8200, GRT 880)
[5 empty] | 1 |  | Excavator (CAT 315)
[5 empty] | 1 |  | 2000 Gal Water Truck
[5 empty] | 1 |  | Skidsteer (JD 331)
[5 empty] | 1 |  | Loader (CAT 966)
[5 empty] | 1 |  | Segment Forklift (Hyundai 250D-9)
[5 empty] | 1 |  | Telehandler (GEHL RS9-50)
[5 empty] | 1 |  | Manlift (Skyjack SJ63AJ)
[5 empty] | 4 |  | Multi Service Vehicles
Subcontractors |  |  |  |  | Shift Start: |  | 14:00 | Shift End: | 22:00
TEI- TBM Electrical |  |  |  |  | Equipment (Rental)
[5 empty] | No. |  | Description
[5 empty] | 1 |  | Telehandler 10,000Lb
[5 empty] | 1 |  | Telehandler 6,000Lb
Accidents
Zero Accident & Zero Injuries
Special Tests/Inspection
Superintendent Signature
Michael Leslie
Additional Notes