## DAILY
Company: | Dragados | [5 empty] | Date: | 04/09/2024
Project: | JWPCP Effluent Outfall Tunnel | [5 empty] | Weather: | Sunny |  |  | DAY | #REF!
Location: | JWPCP Site | [5 empty] | Site Conditions: | Normal
|  | No. of Days Worked on Project: | 1368 |  |  |  | Temp: | 76
[12 empty] | 1 | 2 | 3 | #REF!
Dragados Staff* |  |  | Dragados Personnel |  |  |  | Subcontractors Onsite |  |  |  | Description | DAY | SWING | GRAVEYARD | MISSING (-)
Office Staff | 1 |  | Foreman | 1 |  |  | WA RASIC | 0 |  |  | Foreman | 1 | 1 | 1 |  | 1
Field Staff | 2 |  | Operators | 6 |  |  | TENSA | 0 |  |  | Electricians | #REF! | #REF! | #REF! |  | 6
Safety | 1 |  | Laborers | 8 |  |  | TEI | 2 |  |  | Laborers | #REF! | #REF! | #REF! |  | 15
|  |  | Cr Operators | 1 |  |  | Sixense | 0 |  |  | Gas Tester | #REF! | #REF! | #REF! |  | 1
|  |  | Mechanics | 3 |  |  | Landmark | 0 |  |  | Mechanics | #REF! | #REF! | #REF! |  | 4
|  |  | Oiler | 1 |  |  | Guard | 1 |  |  | Operators | #REF! | #REF! | #REF! |  | 1
|  |  | Gas Tester | 1 |  |  | District | 1 |  |  | Cr Operator | #REF! | #REF! | #REF! |  | 1
|  |  | Surveyor | 1 |  |  | HK | 0 |  |  | Oiler | #REF! | #REF! | #REF! |  | 1
[7 empty] | Ballard | 0 |  |  | Surveyor | #REF! | #REF! | #REF!
Dragados Production Details |  |  |  |  | Shift Start: |  | 14:00 | Shift End: | 22:00
Description of Work Performed |  |  |  |  | TBM ADVANCE | [11 empty] | r
TBM/Tunnel/STP Advance: 4351, 4352*, 4353, 4354, 4355, 4356 Ring Build: 4351, 4352*, 4353, 4354, 4355, 4356 -Performed vacuum test on erector and segment hoist both passed. -Performed daily mechanical TBM checks. -Drilled grout ports 1 and 3. -Extended slurry at 4352, and all utilities. -R/R oil from oiler at T/S pump #2. -R/R oil from oiler at EP2 pump. -R/R oil from oiler at HBW pump. -Greased P1.5 bearing impeller/motor. -Checked oiler at P2.1. -Checked oil level and oiler at P1.5. -Checked oil level waste water pump. -Checked oil level dewatering pump. -Started moving the navigation laser forward. -Cleaned the building area throughout the night. -Repaired waste pump for filter press #3. -Cleaned wet silo for filter press #1 (ongoing). -Brought in 3 totes of polymer. -Tail Seal Grease average: 486mm per push ( 68% of a barrel). 50% 214/ 50% Alcohol 4351: 375.42 gallons, 4352: 410.98 gallons, 4353: 316.40 gallons, 4354: 297.2 gallons, 4355: 282.6 gallons, 4356: 338.8 gallons |  |  |  |  | START STA |  | 218+34.16
[5 empty] | END STA |  | 218+63.65
[6 empty] | SHIFT |  | DAILY TOTAL
[5 empty] | ADVANCE | 6 |  | 7 |  | 1
[5 empty] | RINGS BUILT | 6 |  | 7 |  | 1
[5 empty] | PT THREADED | 0 |  | 0 |  | 0
[5 empty] | PT TENSIONED | 0 |  | 0 |  | 0
[5 empty] | PT GROUTED | 0 |  | 0 |  | 0
TBM GREASE CONSUMPTION
[5 empty] | Grease Station | Δ Filling Level (mm) |  | Weight (KG)
[5 empty] | TSG 1 | 1490 |  | 528.3688
[5 empty] | TSG 2 | 1430 |  | 507.0922
[5 empty] | EP2 | 420 |  | 113.1915
[5 empty] | HBW | 350 |  | 114.1844
Equipment
[5 empty] | No. |  | Description
[5 empty] | 2 |  | Crane (Liehberr 8200, GRT 880)
[5 empty] | 1 |  | Excavator (CAT 315)
[5 empty] | 1 |  | 2000 Gal Water Truck
[5 empty] | 1 |  | Skidsteer (JD 331)
[5 empty] | 1 |  | Loader (CAT 966)
[5 empty] | 1 |  | Segment Forklift (Hyundai 250D-9)
[5 empty] | 1 |  | Telehandler (GEHL RS9-50)
[5 empty] | 1 |  | Manlift (Skyjack SJ63AJ)
[5 empty] | 4 |  | Multi Service Vehicles
Subcontractors |  |  |  |  | Shift Start: |  | 14:00 | Shift End: | 22:00
TEI- TBM Electrical |  |  |  |  | Equipment (Rental)
[5 empty] | No. |  | Description
[5 empty] | 1 |  | Telehandler 10,000Lb
[5 empty] | 1 |  | Telehandler 6,000Lb
Accidents
Zero Accident & Zero Injuries
Special Tests/Inspection
Superintendent Signature
Michael Leslie
Additional Notes